## Sheet1
Project Name | Multimedia Image processing using OpenCV
Demo Ready date: | 2016-10-25
Project Objective | The main objective of this project is, to identify the person using OpenCV Library.
Phase objective | Python libraries for captured Image
Developers | Sandeep A,Ramya D, Sandeep G, Ashok P, Deepika P, Anjaneyulu R, Rathod R
Testers | Meena P, Srinivasarao G, Dayanand P, Rahul C,Nagma B
Cost of the Project
Achievements Till now | 1.Able to browse image from local directory, and able to detect the face using haar algorithm. 2.Able to take image from connected camera(using droidcam) and able to detect the face 3.wrote 25 testcases.
Project Phase and Deliverables | October List | Planned for November
| GUI Application | Camera Driver
| Face Detection Module | Image Processing
| Database server Creation | Image Comparison
search more algorithms to detect face
Skills upgraded | Python
Mysql
debugging skills
writing test cases
New Skills | OpenCV(haar algorithm)
image processing
Total Lines of code added | 100 lines
Total test cases added | 25
GITHUB link | git clone rathod@192.168.4.190:~ /Multimedia_OpenCV Password: multimedia1234
Remarks and Information | Need help to write camera driver Need training for Yocto and Linaro

## New Skill
New Skills
| OpenCV (Haar Algorithm): | Sandeep A,Ramya D, Sandeep G, Ashok P, Deepika P, Anjaneyulu R, Rathod R
Meena P, Srinivasarao G, Dayanand P, Rahul C,Nagma B